SustainSME — Product Workplan

SME Decarbonization Platform  |  May 25 – Jul 17, 2026 |  8 weeks  |  6 hrs/day

1 week behind

  Frontend: ready by end of May

  Stakeholder review (Frontend): first week of June

  Backend development: starts thereafter

| June 8 2026 Start Date | Fri Jul 17, 2026 Completion | 8 weeks Duration | ~210 hrs + 1 week buffer Total effort | Claude Tool |
| --- | --- | --- | --- | --- |

| # | Phase | Start | End | Duration | Key Activities |
| --- | --- | --- | --- | --- | --- |
| 01 | Prototype from Figma Wireframes On Claude — no deployment | Mon 25 May 2026 | Wed 27 May 2026 | 3 days | - Build shared components in Claude: navbar, radio group, progress stepper, category badge, Excel card, upload trigger, buttons — built once, reused across all screens - Build Scope 3 Category Relevance screen: 15 categories, Yes/No radio buttons per row, Next button enables when all answered - Build Scope 3 questionnaire template (Category 1 full version): progress stepper, two gating questions, conditional Excel download + upload section that appears only when both questions answered Yes - Replicate template for Categories 2–15 — each takes ~15 mins as same component with different text (not 2 hrs each) - Build Scope 1 and Scope 2 input screens, company onboarding, login, dashboard - Build results screens with dummy data: emissions dashboard (Recharts bar chart), ESG score gauge, decarbonisation lever cards, PDF report preview - Wire all screen navigation — clicking any button routes to the correct next screen - All screens run as a React artifact inside Claude — interactive, click-through, no hosting needed ⚑ Hosted directly in Claude. No Vercel, no GitHub, no installation. Screen-share from your laptop for the stakeholder call. |
| 02 | Gap Analysis & Additional Screens Still in Claude | Thu 28 May 2026 | Fri 29 May 2026 | 2 days | - Review the prototype against the full product vision — list screens that are missing or need refinement - Identify gaps: consultant portfolio view, admin panel, onboarding flow edge cases, mobile input patterns - Build additional screens in Claude, add to the existing React artifact - Add dummy data variations so dashboards show realistic numbers and charts across different company types - Final prototype covers complete product vision, all user journeys clickable end-to-end |
| 03 | Stakeholder Review (Nina + Team) Single day | Mon 1 Jun 2026 | Mon 1 Jun 2026 | 1 day | - Morning: screen-share the Claude prototype in a 1-hour structured session — walk through all three user journeys live - Capture all feedback in real time: what is missing, what needs to change, what is the priority order - Afternoon: sort feedback with the team into must-fix / v1 / v2 backlog. Make quick visual changes to the prototype on the spot - Confirm direction and agreed scope before methodology and build work begins ⚑ Gate — backend build does not start until direction is confirmed. Single day is sufficient because the prototype is already interactive and tangible. |
| 04 | Emission Methodology & Logic Definition Analysis work — not coding | Tue 2 Jun 2026 | Fri 12 Jun 2026 | 1.5 weeks | - Document the actual calculation formulae for Scope 1 (stationary combustion, mobile combustion, fugitive emissions), Scope 2 (location-based and market-based electricity), and all 15 Scope 3 categories - Define which calculation method applies per Scope 3 category: spend-based, average-data, distance-based or primary data — and under what data availability conditions each is used - Source, validate and format all emission factor datasets: GHG Protocol Scope 1/2 factors, IEA grid emission factors by country, EPA Scope 3 spend-based factors - Define the ESG scoring framework: KPI list, materiality weights by sector, score formula (0–100), E/S/G sub-score structure - Define peer benchmarking methodology: percentile ranking formula, sector average sources, top quartile comparison - Define the gap-filling logic: what default values apply when a company has no data for a category, and how estimated values are flagged - This document becomes the specification the backend code implements — calculation code written without this spec will need to be rewritten ⚑ This is analytical and methodological work, not development. Requires someone with sustainability/carbon accounting knowledge to validate. Do not skip or compress this phase. |
| 05 | Backend & Calculation Engine Supabase — browser dashboard + Claude code | Mon 15 Jun 2026 | Fri 26 Jun 2026 | 2 weeks | - Set up Supabase project: database, authentication, file storage — all configured via browser dashboard, no installation - Create all database tables from schema: companies, assessments, scope inputs (1/2/3), results, ESG scores, sector benchmarks, emission factors, levers - Seed all emission factor data, sector benchmarks and lever library into the database - Build Scope 1 calculator (Edge Function): stationary + mobile combustion + fugitives - Build Scope 2 calculator: electricity (location-based and market-based) + purchased heat - Build Excel parsing engine: reads uploaded .xlsx files, validates columns, returns structured data — used by all 15 Scope 3 categories - Build Scope 3 calculators (one per category): spend-based, average-data and distance-based methods as defined in Phase 4 methodology - Build ESG scoring function and peer benchmarking engine - Build decarbonisation lever recommendation engine - Build PDF report generation |
| 06 | Frontend–Backend Integration Connect React prototype to Supabase | Mon 29 Jun 2026 | Fri 3 Jul 2026 | 1 week | - Add Supabase client to the React app (single npm install step) - Connect every form and action to real API calls: login, company profile, Scope 1/2/3 inputs, Excel file upload, calculation trigger, results, ESG score, levers, PDF download - Replace all dummy data and placeholder numbers with live results from the calculation engine - Connect consultant portfolio and admin panel to real database queries - Full end-to-end test: sign up → complete full assessment → download PDF report |
| 07 | Testing & Deployment Real users + Accenture staging | Mon 6 Jul 2026 | Fri 17 Jul 2026 | 2 weeks | - User testing with 2–3 real users: one SME with data, one with limited data, one consultant — observe full journeys without assistance - Log all issues, fix critical ones, log medium/low for v1.1 - Deploy to Accenture staging server (IT request must be submitted Week 1-2 — provisioning takes 1–3 weeks) - End-to-end test on Accenture staging URL — verify file uploads, calculations, PDF generation all work on the hosted environment - Share staging URL with Nina and the wider team ⚑ Accenture IT request must be submitted Week 1 (May 4). Provisioning takes up to 3 weeks — this is the one dependency outside the developer's control. |
| TOTAL ¦ May 4 – Jun 26, 2026 ¦ 8 weeks |  |  |  |  | ~210 hrs estimated ¦ 245 hrs capacity (7 wks × 5 days × 6 hrs) ¦ ~35 hrs buffer |

| Why the prototype takes 3 days, not 2 weeks The Scope 3 questionnaire screens (15 of them) are a single React component with different text — not 15 separate builds. Once Category 1 is built, Categories 2–15 take ~15 minutes each. The screens in the Figma are genuinely simple: mostly radio buttons, labels and a conditional file upload section. The dashboard screens are more complex but Claude generates Recharts charts directly from a description. | Why Phase 4 (Methodology) cannot be compressed Writing the emission calculation logic is not a coding task — it is a carbon accounting task. The formulae, emission factors, calculation methods and gap-filling assumptions need to be defined and validated by someone with sustainability knowledge before any backend code is written. Code written without this spec will need to be rewritten. This phase should not be skipped or merged into the build phase. | The one external dependency: Accenture IT The Accenture staging server must be requested in Week 1 (May 4). IT provisioning takes 1–3 weeks and is outside the developer's control. All phases 1–6 run entirely on Claude + Supabase and are not blocked by this. Only Phase 7 (deployment) requires the Accenture server. Submit the request immediately and follow up weekly. |
| --- | --- | --- |